PROGRAM IMPLEMENTATION PLAN

# PROGRAM/PROJECT PROFILE:

| PROGRAM TITLE | DIVISION-LEVEL HUMAN RESOURCE MERIT PROMOTION AND SELECTION BOARD (HRMPSB) ASSESSORS TRAINING ON EXPANDED CAREER PROGRESSION SYSTEM FOR TEACHERS: DEEPENING ON INITIAL EVALUATION AND PHILIPPINE PROFESSIONAL STANDARDS FOR TEACHERS (PPST) ASSESSMENT |
| --- | --- |
| RATIONALE | The issuance of the Executive Order (EO) No. 174, s. 2022 titled “Establishing the Expanded Career Progression System for Public School Teachers” and its Implementing Rules and Regulations (IRR) further reinforce the Department’s commitment in promoting professional development and career advancement among public school teachers. It clearly defines the career paths of teachers within the public school system at the basic education level, attaching their progression with the attainment of the necessary qualifications and professional standards. Congruent with this commitment and in anticipation for the implementation of the Expanded Career Progression (ECP) System, and following the recently concluded National Assessors Training of Trainers (NTOT) and Regional Assessors Training of Trainers (RTOT), and the call of Central Office through the BHROD, the Schools Division Office of Biliran through the Human Resource Development Section shall conduct Training for Human Resource Merit Promotion and Selection Board (HRMPSB) Assessors on Expanded Career Progression which aims to capacitate our HRMPSB and its sub-committees for the implementation of the ECP System. The training focuses on the deepening on the initial evaluation and understanding of teacher’s competency assessment anchored on the Philippine Professional Standards for Teachers (PPST) assessment at the Division level. |
| PROGRAM OUTCOME | To capacitate our HRMPSB and its sub-committees for the implementation of the ECP System. The training focuses on the deepening on the initial evaluation and on the understanding of teacher’s competency assessment anchored on the Philippine Professional Standards for Teachers (PPST) assessment. |
| MAJOR FINAL OUTPUT | The participants are expected to: - Discussed the salient points of EO 174 and the reclassification process - Discussed the Standard-based career progression systems, teacher reclassification and promotion process, assessor’s program, and their duties and responsibilities as assessors; - Evaluated the achievement of the qualification and performance requirements of applicants - Applied the increments table, rubric, and formula in computing the scores on Education, Training, and Experience (ETE), and Performance - Simulated the assessment of Classroom Observable Indicators (COI) and Non-Classroom Observable Indicators (NCOI) - Applied the S.T.A.R. approach in conducting the BEI |

# PROFILE OF TARGET PARTICIPANTS

| Target Job Groups | SCHOOLS DIVISION SUPERINTENDENT, ASSISTANT SCHOOLS DIVISION SUPERTINDENT, CID CHIEF, SGOD CHIEF, ADMINSTRATIVE OFFICE V, HRMO, EDUCATION PROGRAM SUPERVISORS, PSDS, SEPS, EPS II, AND NON-TEACHING PERSONNEL |
| --- | --- |
| Total Number of Participants | 48 |

Breakdown of participants:

| School Leaders |  |  |  |
| --- | --- | --- | --- |
| Region | Division | Position | Number of Participants |
|  | Office of the Schools Division Superintendent | 1- SDS 1- ASDS 1- Administrative Officer V 1 – HRMO 3 - Secretariat | 7 |
|  | Office of the Curriculum Implementation Division | 1 – Chief 8 – EPS 14 - PSDS | 23 |
|  | Office of the Schools Governance and Operations Division | 1 – Chief 4 – SEPS 1 – Planning Officer 2 – EPS II | 8 |
|  | Others | 6- Resource Speakers 2-TWG 2-HNU | 10 |

# IMPLEMENTATION PLAN

The following activities will lead to producing the Major Final Output:

|  | ACTIVITIES | MODALITY & DELIVERY PLATFORM | ACTIVITY OBJECTIVE | ACTIVITY OUTPUT | PARTICIPANTS | NO. OF PAX | NO OF DAYS | TARGET DATE/S, MONTH | PROPOSED VENUE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Procurement Process | Face to Face | Select the training venues that are accessible and equipped with necessary facilities | The venue, food, and supplies for the conduct of the activity were procured | PMT, BAC | N/A | 30 working days | July 2025 | n/a |
|  | Pre-Planning Conference with the PMTs and RPs | Face to Face | Select and assign trainer/resource persons who have the expertise in delivering effective training sessions Provide trainers with comprehensive training materials, facilitation guides, and support to ensure consistency in delivery. | DM Crafted and disseminated | PMT | 15 | 1 day | Aug. 2025 | SDO Biliran Conference Hall |
|  | Conduct of DIVISION-LEVEL HRMPSB ASSESSORS TRAINING ON EXPANDED CAREER PROGRESSION SYSTEM FOR TEACHERS: DEEPENING ON INTIAL EVALUATION AND PPST ASSESSMENT | Face to Face | Conduct interactive training sessions on Expanded Career Progression to participants and encourage active participation. | Conduct of DIVISION-LEVEL HRMPSB ASSESSORS TRAINING ON EXPANDED CAREER PROGRESSION SYSTEM FOR TEACHERS: DEEPENING ON INTIAL EVALUATION AND PPST ASSESSMENT | SDS, ASDS, Admin Officer, Chief, HRMO, EPS, PSDS, SEPS, EPS II | 48 | 2 days | Sept. 18-19, 2025 | To be Determined |
|  |  | Face to Face | Conduct assessment to measure participants’ understanding and feedback regarding the content, delivery, and effectiveness. Use evaluation data to identify areas for improvement and adjust on the next training sessions | Daily Evaluation | PMT | 15 | 2 days | Sept 18-19, 2025 | To be determined |
|  | Daily Debriefing Sessions |  |  |  |  |  |  |  |  |
|  | Post Training | Face to Face | Offer follow-up support and resources to help participants apply their |  | PMT | 15 | 1 day | Sept. 22, 2025 |  |
|  | Conference |  | learning in | Program Completion Report |  |  |  |  |  |
|  |  |  | the field. Facilitate opportunities for collaboration and knowledge sharing among educators with the SDO. |  |  |  |  |  |  |

# BUDGET ESTIMATE

| ACTIVITY | NO. OF PAX | EXPENDITURE |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | FOOD | COMMS | VENUE | PROF FEES | SUPPLIES AND MATERIALS | CONTINGENCY | OTHERS | SUBTOTAL |
| Procurement Process | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0.00 |
| Pre-Planning Conference | 15 | 6,750 | n/a | n/a | n/a | n/a | n/a | 16,001.25 | 22,751.25 |
| Conduct of DIVISION-LEVEL HRMPSB ASSESSORS TRAINING ON EXPANDED CAREER PROGRESSION SYSTEM FOR TEACHERS: DEEPENING ON INITIAL EVALUATION AND PPST ASSESSMENT | 48 | (450x48)*2 = 43,200.00 | n/a | (10,000.00)*2 venues = 20,000.00 | n/a | Training materials = 17,048.75 | 5,000 | n/a | 85,248.75 |
| Daily Debriefing Sessions | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0.00 |
| Post-Training Conference | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0.00 |
| TOTAL |  |  |  |  |  |  |  |  | 108,000.00 |

# PROGRAM MANAGEMENT TEAM

| NAME OF PERSONNEL | OFFICE / UNIT | ROLE | TERMS OF REFERENCE |
| --- | --- | --- | --- |
| DR. ROBERTO N. MANGALIMAN, CESO VI | OSDS | Overall Lead | - Oversees the implementation of the entire program. |
| MR ARVIN T. ELATICO, CPA | OSDS |  |  |
| DR. JOSEPHINE M. CASAS | SGOD | Overall Program Manager | - Organizes and supervises the PMT to ensure that all processes are carried out and outputs delivered according to standards. |
| DR. JOSE B. MONDIDO | CID |  |  |
| DR. JOSEPHINE M. CASAS | SGOD | Learning Manager | - Ensures that the program is carried out based on the detailed design in collaboration with the resource persons/ subject- matter experts. |
| MR. JORDAN C. JAMORALIN | HRD | Program Manager | - Oversees the implementation of the entire program. - Organizes and supervises the PMT to ensure that all processes are carried out and outputs delivered according to standards. - Orients the PMT and the resource persons/ subject-matter experts on their terms of reference and the details of the program design. - Leads in conducting debriefing with the PMT and resource speakers/ subject- matter experts. - Prepares the CPD documents for submission to the PRC through the NEAP-R. - Leads in crafting the Program Completion Report. - Prepares and sends a communication to participants’ supervisors - regarding program completion and the importance of implementing the Workplace Application Plan. |
| MR. LOUIE S. CASTIN | HRD | Logistics Officer & Documenter | - Ensures the quality, adequacy, and availability of facilities, equipment, supplies and materials, vehicles, and other resources to support the successful implementation of the program. - Leads ocular inspection of venues to ensure adherence to standards and specifications. - Checks that session rooms are always ready for use and conducive to learning. - Attends to registration needs of learners. - Ensures that learners fill up attendance sheets every day. - Prepares directory of participants based on registration forms. - Assists in the distribution of learning materials and supplies. - Assists in posting and collection of session outputs. - Compiles session documents and learning resource materials. - Documents the proceedings of the learning sessions using the prescribed documentation template. - Takes photos of the different parts of the program delivery. |
| ALADIN P. NIERRAS JORDAN C. JAMORALIN | M&E M&E | M&E Manager M&E Asst. Manager | - Prepares Post-Program Delivery M and E Report and submits to PM for inclusion in the Program Completion Report. - Prepares and implements the Monitoring and Evaluation Plan in collaboration with the PMT. - Assists the Program Manager in accomplishing the Program Delivery Readiness Checklist. - Applies process observation and prescribed tools to monitor and evaluate program delivery. - Administers and analyzes the results of Level 1 evaluation which is to be presented during debriefing. - Assists the Learning Manager in administering and analyzing the results of Level 2 evaluation. - Prepares Post-Program Delivery M and E Report and submits to PM for inclusion in the Program Completion Report. |
| DR. PATRICIA MARIE S. DAYAGBIL | SGOD | Welfare Officer | - Ensures that provisions for inclusion, safety, security, health, and wellness of learners, PMT, and resource persons are adequate and available at all times in the venue. - Attends to emerging inclusion, safety, security, health, and wellness concerns of participants, PMT, and resource speakers/ subject-matter experts (including incidents of social exclusion, sexual harassment, etc.). |
| RESOURCE SPEAKERS | CID/SGOD/ SCHOOLS | Learning Facilitators | - Applies effective presentation and facilitation techniques in conducting assigned sessions. - Provides expert content input during learning sessions. - Applies effective presentation and facilitation techniques in conducting assigned sessions. - Provides expert content input during learning sessions. |

| Prepared by: SCHOOL HEAD | Reviewed by: PSDS Recommending Approval JOSEPHINE M. CASAS, EdD ARVIN T. ELATICO, CPA CES, SGOD OIC- ASSISTANT SCHOOLS DIVISION SUPERINTENDENT |
| --- | --- |
| Approved by: |  |
| ROBERTO N. MANGALIMAN, PhD CESO VI Assistant Schools Division Superintendent OFFICER-IN-CHARGE Office of Schools Division Superintendent |  |